## Cover Page
<Reflex Trainer>
Prepared By:
Team 5
<Abdulla Hareth>: <40212538>
<Ivan Simic-Petrovic>: <40247928>
<Elfried Jeffrey Kamdem Sindjoun>: <40315383>
<Daniel Roikhman>: <40134133>
<Shadman Chowdhury>: <40286231>

## Product Backlog
Product Backlog
PRODUCT BACKLOG: High-Precision Reflex Trainer
Story ID | Story Title | Card | Story Points | Sprint | Status | Conversation | Confirmation
AUTH-1 | User Registration | As a user, I want to create an account so that my personal training history can be securely stored. | 5 | Sprint 1 | Planned | Implement secure user registration using Firebase Authentication. | 1. Can a new user create an account? 2. Is the account stored correctly?
AUTH-2 | User Login | As a user, I want to securely log into my account so that I can access my saved progress. | 5 | Sprint 1 | Planned | Develop a secure login system allowing authenticated access to the application. | 1. Can registered users log in? 2. Are incorrect credentials rejected?
UI-1 | Home Screen | As a user, I want a simple home screen so that I can easily navigate the application. | 5 | Sprint 1 | Planned | Design a clean home page providing access to all major features. | 1. Can users navigate easily? 2. Are all buttons functional?
UI-2 | Sensor Connection Indicator | As a user, I want to know whether the sensor is connected so that I know when the application is ready. | 3 | Sprint 1 | Planned | Display the real-time hardware connection status on the home screen. | 1. Does the indicator update correctly? 2. Is the user notified when disconnected?
HW-1 | Bluetooth Device Discovery | As a user, I want the application to discover nearby reflex sensors so I can connect my device. | 5 | Sprint 1 | Planned | Implement Bluetooth scanning to detect compatible reflex sensors. | 1. Can nearby devices be discovered? 2. Are unsupported devices ignored?
HW-2 | Bluetooth Device Pairing | As a user, I want to pair my reflex sensor with the application so that it can transmit data. | 5 | Sprint 1 | Planned | Develop Bluetooth pairing functionality for supported hardware devices. | 1. Can the device pair successfully? 2. Is the pairing remembered?
HW-3 | Hardware Synchronization | As a user, I want the application to synchronize with the hardware so that reaction events are transmitted instantly. | 8 | Sprint 1 | Planned | Synchronize live hardware events with the Android application. | 1. Is hardware data received correctly? 2. Is synchronization maintained during training?
FUNC-1 | Start Training Session | As a user, I want to start a training session so that I can begin reflex practice. | 5 | Sprint 1 | Planned | Implement the complete workflow required to initialize a new training session. | 1. Does training start correctly? 2. Is the user ready for the stimulus?
FUNC-2 | Stop Training Session | As a user, I want to stop a training session so that I can safely end my practice at any time. | 3 | Sprint 1 | Planned | Provide functionality to terminate an active training session safely. | 1. Can training be cancelled? 2. Is partial data handled correctly?
FUNC-3 | Reaction Time Measurement | As a user, I want my reaction time measured precisely so that I receive accurate performance feedback. | 8 | Sprint 1 | Planned | Measure reaction time using synchronized hardware input with millisecond precision. | 1. Is reaction time calculated correctly? 2. Is the displayed value accurate?
DATA-1 | Local Database Setup | As a user, I want my training data stored locally so that my results remain available without Internet access. | 5 | Sprint 1 | Planned | Configure the local database used to store all application data. | 1. Is the database created successfully? 2. Can data be retrieved after restarting?
DATA-2 | Save Training Results | As a user, I want every completed session saved automatically so that I can monitor my progress. | 5 | Sprint 1 | Planned | Store completed training sessions immediately after they finish. | 1. Are completed sessions saved? 2. Are duplicate entries prevented?
DATA-3 | Training History | As a user, I want to review previous sessions so that I can evaluate my progress. | 3 | Sprint 2 | Planned | Display all previous training sessions in chronological order. | 1. Are all sessions displayed? 2. Can the user scroll through history?
DATA-4 | Delete History | As a user, I want to delete unwanted sessions so that I can manage my stored data. | 3 | Sprint 2 | Planned | Allow users to remove selected training sessions from history. | 1. Can sessions be deleted? 2. Is the database updated correctly?
STAT-1 | Performance Statistics | As a user, I want average, fastest, and slowest reaction times so that I can evaluate my performance. | 5 | Sprint 2 | Planned | Calculate performance statistics using recorded training sessions. | 1. Are averages calculated correctly? 2. Are best and worst values accurate?
STAT-2 | Performance Graphs | As a user, I want graphical representations of my progress so that I can visualize improvements. | 5 | Sprint 2 | Planned | Generate graphs using historical reaction time data. | 1. Are graphs displayed correctly? 2. Do they represent stored data?
FUNC-4 | Difficulty Selection | As a user, I want to select the training difficulty so that the challenge matches my skill level. | 5 | Sprint 2 | Planned | Implement multiple selectable difficulty levels. | 1. Can users change difficulty? 2. Does training behaviour change?
FUNC-5 | Random Stimulus Generation | As a user, I want randomized stimulus timing so that I cannot anticipate the signal. | 5 | Sprint 2 | Planned | Generate randomized stimulus intervals during training. | 1. Are delays random? 2. Are repeated patterns avoided?
HW-4 | Hardware Calibration | As a user, I want to calibrate my sensor before training so that measurements remain reliable. | 5 | Sprint 2 | Planned | Develop a calibration routine to verify hardware accuracy. | 1. Can calibration be completed? 2. Is hardware validated successfully?
HW-5 | Signal Validation | As a user, I want invalid sensor signals detected so that inaccurate measurements are prevented. | 5 | Sprint 2 | Planned | Validate incoming hardware signals before processing them. | 1. Are corrupted signals rejected? 2. Is the user informed?
DATA-5 | Cloud Synchronization | As a user, I want my training history synchronized online so that I can access it from another device. | 8 | Sprint 2 | Planned | Synchronize user training data with Firebase Cloud Database. | 1. Can data upload successfully? 2. Can synchronized data be downloaded?
FUNC-6 | Multiple Training Modes | As a user, I want multiple training modes so that I can improve different reaction skills. | 8 | Sprint 3 | Planned | Implement Classic, Random, and Rapid-Fire training modes. | 1. Can users choose different modes? 2. Does each mode behave differently?
FUNC-7 | AI Training Recommendations | As a user, I want personalized training recommendations so that I know how to improve my performance. | 8 | Sprint 3 | Planned | Generate recommendations based on previous training performance. | 1. Are recommendations personalized? 2. Do they update after training?
USER-1 | User Profile | As a user, I want my own profile so that my personal statistics remain separate from others. | 5 | Sprint 3 | Planned | Create individual user profiles linked to authenticated accounts. | 1. Can users access their own profiles? 2. Is profile data isolated?
USER-2 | Friends & Challenges | As a user, I want to connect with friends so that we can compare scores and complete challenges together. | 8 | Sprint 3 | Planned | Develop a social challenge system for sharing scores and competing with friends. | 1. Can users add friends? 2. Can challenge invitations be sent?
UI-3 | Settings Screen | As a user, I want configurable settings so that I can personalize the application. | 3 | Sprint 3 | Planned | Provide configurable application preferences such as notifications and sound. | 1. Can settings be modified? 2. Are preferences saved?
UI-4 | Dark Mode | As a user, I want dark mode support so that the application is comfortable to use in low-light environments. | 3 | Sprint 3 | Planned | Implement an alternative dark interface theme. | 1. Can dark mode be enabled? 2. Is every screen updated correctly?
USER-3 | Achievement System | As a user, I want to unlock achievements so that my progress is rewarded and motivating. | 5 | Sprint 3 | Planned | Create achievement badges based on training milestones. | 1. Are achievements unlocked correctly? 2. Are badges permanently saved?
UI-5 | Push Notifications | As a user, I want reminders to train so that I stay consistent with my practice schedule. | 3 | Sprint 3 | Planned | Send scheduled notifications encouraging regular training sessions. | 1. Are notifications received? 2. Can users disable them?

## Sprint 1
Sprint 1 Backlog
Story ID | Task ID | Task Title | Task Description | Ideal Hours | Status | Comments
AUTH-1 | AUTH-1.1 | Configure Firebase | Configure Firebase project and enable Authentication. | 4 | Planned | Required before authentication features.
AUTH-1 | AUTH-1.2 | Registration Screen | Design and implement the registration page. | 5 | Planned | Follow application wireframes.
AUTH-1 | AUTH-1.3 | Validate Registration | Validate user information before account creation. | 3 | Planned | Check email and password format.
AUTH-2 | AUTH-2.1 | Login Screen | Design and implement the login page. | 5 | Planned | Maintain consistent UI.
AUTH-2 | AUTH-2.2 | User Authentication | Authenticate users using Firebase Authentication. | 5 | Planned | Verify valid credentials.
UI-1 | UI-1.1 | Home Screen | Design and implement the application's home screen. | 5 | Planned | Entry point after login.
UI-1 | UI-1.2 | Navigation | Implement navigation between Home and Training pages. | 4 | Planned | Navigation should remain intuitive.
UI-2 | UI-2.1 | Connection Status | Display hardware connection status on the home screen. | 3 | Planned | Green = Connected, Red = Disconnected.
HW-1 | HW-1.1 | Bluetooth Discovery | Discover compatible Bluetooth reflex sensors. | 5 | Planned | Scan nearby supported devices.
HW-1 | HW-1.2 | Device Selection | Display discovered devices & allow user selection. | 3 | Planned | List only compatible devices.
HW-2 | HW-2.1 | Bluetooth Pairing | Pair selected Bluetooth device with the application. | 5 | Planned | Maintain secure pairing.
HW-2 | HW-2.2 | Automatic Reconnection | Automatically reconnect old paired devices. | 3 | Planned | Improve usability.
HW-3 | HW-3.1 | Receive Hardware Events | Receive live hardware events from the external sensor. | 5 | Planned | Core communication feature.
HW-3 | HW-3.2 | Synchronize Data | Synchronize hardware events with the application timer. | 5 | Planned | Minimize communication delay.
HW-3 | HW-3.3 | Validate Sensor Communication | Verify integrity of incoming hardware data. | 3 | Planned | Ignore corrupted packets.
FUNC-1 | FUNC-1.1 | Start Training | Implement Start Training button functionality. | 3 | Planned | Initialize training session.
FUNC-1 | FUNC-1.2 | Initialize Training | Prepare timers, variables, and hardware before training. | 4 | Planned | Reset previous session data.
FUNC-2 | FUNC-2.1 | Stop Training | Allow users to safely terminate an active session. | 3 | Planned | Save completed progress.
FUNC-3 | FUNC-3.1 | Reaction Timer | Implement high-precision reaction timer. | 5 | Planned | Millisecond precision required.
FUNC-3 | FUNC-3.2 | Display Reaction Time | Display reaction time immediately after each attempt. | 3 | Planned | User feedback.
DATA-1 | DATA-1.1 | Local Database | Configure local database structure for application data. | 5 | Planned | Store users and sessions.
DATA-1 | DATA-1.2 | Database Testing | Verify database creation & read/write operations. | 3 | Planned | CRUD verification.
DATA-2 | DATA-2.1 | Save Session | Save completed training sessions automatically. | 4 | Planned | Store timestamp and reaction time.
DATA-2 | DATA-2.2 | Verify Stored Data | Verify saved session data after application restart. | 3 | Planned | Ensure persistence.
ADMIN-1 | DOC-1 | Product Backlog Update | Update Product Backlog after Sprint Planning meeting. | 3 | Planned | Reflect latest sprint decisions.
ADMIN-2 | DOC-2 | Sprint Backlog Update | Update Sprint Backlog with finalized Sprint 1 tasks. | 3 | Planned | Keep backlog synchronized.
ADMIN-3 | DOC-3 | Sprint Documentation | Prepare Sprint 1 documentation and meeting notes. | 4 | Planned | Documentation required for submission.
ADMIN-4 | DOC-4 | Git Repository Setup | Create Git repository, branching strategy and project structure. | 4 | Planned | Shared repository for all members.
ADMIN-5 | DOC-5 | Team Sprint Meeting | Conduct Sprint Planning meeting and assign responsibilities. | 3 | Planned | Ensure all members understand tasks.
|  |  | Category | Hours
|  |  | Authentication | 22
|  |  | User Interface | 12
|  |  | Hardware Integration | 24
|  |  | Core Functionality | 18
|  |  | Database | 15
|  |  | Documentation / Project Management | 17
|  |  | Total | 108 Hours
Sprint 1 Goal(s): |  | 1.Establish the core architecture of the High-Precision Reflex Trainer application.
2. Implement secure user registration and authentication using Firebase Authentication.
3. Develop Bluetooth communication to discover, pair, and synchronize the external reflex sensor with the Android application.
4. Implement the core training workflow, including starting and stopping training sessions and accurately measuring user reaction times.
5. Design and implement the main user interface, including navigation and real-time sensor connection status.
6. Configure a local database to securely store user information and training session results.
7. Complete Sprint 1 documentation, update the Product and Sprint Backlogs, and prepare the project foundation for future sprint development.